## Sprint Planning
Project Backlog
CSE-6324 - AGILE 2022
Project Name:Trade-BnB | Web Application
Team Members: Abhinav Wadhwa, Pankaj Venkat Gope, Manish Kumar, Hardik Jain, Prithviraj Eswaramoorthy, Lu Wen, Shalabh Bajaj
Sprint | Story | No. Of Days | Status | Team Structure | Total Story Points=Total days of work | 50
SP1 | Login Page | 2 | TBS | Scrum:Manish | Total Sprints | 5
| Registration Page | 2 | TBS | Pair1: Prithviraj and Abhinav
| Dashboard/Landing Page | 2 | TBS | Pair2: Hardik and Pankaj | Total Sprints | Forecast-Days | Actual-Days
| Stack and Infra Planning | 1 | TBS | Pair3: Lu Wen & Shalabh | 1 | 50 | 43
| Data Island | 2 | TBS |  | 2 | 40 | 33
| Testing | 1 | TBS |  | 3 | 30 | 23
SP2 | Navigation/Roles/Routing | 3 | TBS | Scrum:Hardik | 4 | 20 | 13
| Verification/Validation | 2 | TBS | Pair1: Prithviraj and Lu Wen | 5 | 10 | 3
| Session State/cookies | 2 | TBS | Pair2: Shalabh and Pankaj
| Dashboard(Flashcards and features) | 2 | TBS | Pair3: Manish & Abhinav
| Testing | 1 | TBS
SP3 | F1 - Orders | 3 | TBS | Scrum:Abhinav
| F2 - Funds | 1 | TBS | Pair1: Shalabh and Lu Wen
| F3 - Portfolio | 2 | TBS | Pair2: Prithviraj and Pankaj
| F4 -Active Positions | 1 | TBS | Pair3: Manish & Hardik
| F5 - DJ/S&P500/Nasdaq | 2 | TBS
| Testing | 1 | TBS
SP4 | F6 - Markets | 3 | TBS | Scrum:Pankaj
| F7 - History | 2 | TBS | Pair1: Manish and Lu Wen
| F8 - Fund Transfer | 2 | TBS | Pair2: Hardik and Shalabh
| F9 - Alerts | 1 | TBS | Pair3: Abhinav & Prithvi
| F10 Settings | 1 | TBS
| Testing | 1 | TBS
SP5 | F11 Documents | 1 | TBS | Scrum:Prithviraj
| F12 Help Center | 1 | TBS | Pair1: Lu Wen and Abhinav
| F13 Forum | 3 | TBS | Pair2: Hardik and Pankaj
| F14 Messages | 1 | TBS | Pair3: Manish & Shalabh
| F15 Payment Gateway | 3 | TBS
| Testing | 1 | TBS

## Sheet2
Sprint 1
Start Date – End Date: | Feb. 14, 2022 – Feb. 25, 2022
ScrumMaster Name: | Manish Kumar
Pair 1 members: | Shalebh, wen,Lu
Pair 2 members: | Prithviraj, Abhinav
Pair 3 members: | Hardik, Pankaj
Number of Stories: | 6'
Story 1: | Story Title: Login Page Long Description:
Story 2: | Story Title: Registration page Long Description: Create the registration page with fields such as name, age, email, phone number, username, password and confirm password. • After the user submits the registration form, an email will be sent to the registered email id. • User can confirm their registration by clicking on the confirmation link in the email.(In real world users are not registered until they provide a valid SSN and Bank Account number, which is sent as a seperate secure form for the user to fill after initial verification)
Story 3: | Story Title: Dashboard/Landing Page Long Description: The dashboard here refers to implementing the overall app layout:a) Create headers,b)Create footers,and c)Create Features layout.
Story 4: | Story Title: System Design Long Description: a) Backend, b) Business logic layer, c) Gateway design, d) Frontend
Story 5: | Story Title: Data Island Long Description: Create data mockup for : Frontend/Middle ware/Data dump for backend
Story 6: | Story Title: Testing Long Description: Unit/Integration/regression testing;

## Sheet1
Project Backlog
CSE-6324 - AGILE 2022
Project Name:Trade-BnB | Web Application
Team Members: Abhinav Wadhwa, Pankaj Venkat Gope, Manish Kumar, Hardik Jain, Prithviraj Eswaramoorthy, Lu Wen, Shalabh Bajaj
Sprint | Story | No. Of Days | Status {TBC=To be Scheduled IP= In progress, or C = Complete} | Team Structure
SP1 | Login Page | 2 | TBS | Scrum:Manish
| Registration Page | 2 | TBS | Pair1: Prithviraj and Abhinav
| Dashboard/Landing Page | 2 | TBS | Pair2: Hardik and Pankaj
| Stack and Infra Planning | 1 | TBS | Pair3: Lu Wen & Shalabh
| Data Island | 2 | TBS
| Testing | 1 | TBS
SP2 | Navigation/Roles/Routing | 3 | TBS | Scrum:Hardik
| Verification/Validation | 2 | TBS | Pair1: Prithviraj and Lu Wen
| Session State/cookies | 2 | TBS | Pair2: Shalabh and Pankaj
| Dashboard(Flashcards and features) | 2 | TBS | Pair3: Manish & Abhinav
| Testing | 1 | TBS
SP3 | F1 - Orders | 3 | TBS | Scrum:Abhinav
| F2 - Funds | 1 | TBS | Pair1: Shalabh and Lu Wen
| F3 - Portfolio | 2 | TBS | Pair2: Prithviraj and Pankaj
| F4 -Active Positions | 1 | TBS | Pair3: Manish & Hardik
| F5 - DJ/S&P500/Nasdaq | 2 | TBS
| Testing | 1 | TBS
SP4 | F6 - Markets | 3 | TBS | Scrum:Pankaj
| F7 - History | 2 | TBS | Pair1: Manish and Lu Wen
| F8 - Fund Transfer | 2 | TBS | Pair2: Hardik and Shalabh
| F9 - Alerts | 1 | TBS | Pair3: Abhinav & Prithvi
| F10 Settings | 1 | TBS
| Testing | 1 | TBS
SP5 | F11 Documents | 1 | TBS | Scrum:Prithviraj
| F12 Help Center | 1 | TBS | Pair1: Lu Wen and Abhinav
| F13 Forum | 3 | TBS | Pair2: Hardik and Pankaj
| F14 Messages | 1 | TBS | Pair3: Manish & Shalabh
| F15 Payment Gateway | 3 | TBS
| Testing | 1 | TBS

## SP1
Start Date - Feb. 10 | End Date - Feb. 24
Login Page | Registration Page | Dashboard/Landing Page | System design | Data Island | Testing
US_01: Create a login page with username and password fields. US_02: User should only be able to access the application on login. US_03: Authenticate the user with the registered username and password. US_04: Implement the forgot password functionality. US_05: Allow the user to login using gmail account.(2 way authentication - prefered) | US_06: Create the registration page with fields such as name, age, email, phone number, username, password and confirm password. •US_07: After the user submits the registration form, an email will be sent to the registered email id. US_08: User can confirm their registration by clicking on the confirmation link in the email.(In real world users are not registered until they provide a valid SSN and Bank Account number, which is sent as a seperate secure form for the user to fill after initial verification) | US_08: The dashboard here refers to implementing the overall app layout:a) Create headers,b)Create footers,and c)Create Features layout. | US_09: a) Backend, b) Business logic layer, c) Gateway design, d) Frontend | US_10: Create data mockup for : Frontend/Middle ware/Data dump for backend | Unit/Integration/regression testing;
* Automation - if possible
Scrum:Manish
Pair1: Prithvi and Abhinav
Pair2: Hardik and Pankaj
Pair3: Lu Wen & Shalabh
Sprint Burndown Stats
Sp Start Date | 2022-02-10 | Days of sprint | Forecast | Target | Actual
Sp End Date | 2022-02-24 | 0 |  | 320
Working Days | 10 | 1 |  | 288
Team Size | 7 | 2 |  | 256
working hours per day | 4 | 3 |  | 224
Total Available Hours | 280 | 4 |  | 192
Avg Daily Hours | 40 | 5 |  | 160
Avg Productivity % | 80 | 6 |  | 128
Productive hours | 320 | 7 |  | 96
Avg dDaily Productive Hours | 32 | 8 |  | 64
|  | 9 |  | 32
|  | 10 |  | 0

## SP2
Start Date - Feb. 25 | End Date - Mar. 10
Navigation/Roles/Routing | Validation | Session State/cookies | Dashboard(Flashcards and features) | Testing
Create Navigation, Provide access based on roles/priviliges; setup routing schema between pages pased on priviliges | Validate a user: name - should only contain upper and lower case letters. Two separate fields for given name and Surname age - should only contain numeric values email - must be a valid email (eg. user@domain.com) phone number - should only contain numeric values (length 10 characters) username - must be unique, should only contain alphabets or numbers password - min 8 chars, must be a combination of alphabets, numeric and special characters(passwords are masked at all times) confirm password - this value must match with the password field | Maintain session state using jpt-tokens. Validity till infinity(feature with auto renewal) | Watchlist - available at all times towards the right.(Page layout 70:30) - can have upto 10 using add button and a name for each watch list. Within each watch list can add upto 20 elements. Dedicated shortcuts/Overview to Account Summary, Orders, Current positions, Infographics for - DJ,S&P,NQ/ Breaking news impacting stocks in action(active by volume/value) It should be customizable to Add/Del other elements | Unit/Integration/regression testing;
Scrum:Hardik
Pair1: Prithvi and Lu Wen
Pair2: Shalabh and Pankaj
Pair3: Manish & Abhinav

## SP3
Start Date - Mar. 18 | End Date - Mar. 31
F1 - Orders | F2 - Funds | F3 - Portfolio | F4 -Active Positions | F5 - DJ/S&P500/Nasdaq | Testing
Create a Tab for Pending Orders - Grid: Symbol/(Sell - Buy)/(Limit-Mkt)/Qty/Price/Time/Status(Open-inprogress-completed/close) | Create Pay-In/Pay-Out Controls which redirect to third party payment gateway links | Create Tabs: Current Holdings(number count), Holdings(number count); Create Radio buttons to switch between : Netwise/Daywise (Only Appears for Positions tabs for day trade executions) Create Radio buttons to switch between : MtM/PNL Basic sort by clicking on either column in grid. Create Grid That has columns : Symbol, product, Qty, Prev. Close, LTP, MTM, Buy Avg., Sell Avg The bottom footer shows total MTM for the day | Dashboard shortcut for active positions, Total Investment vs Total PNL, Infographics for performance of portfolio over (Day/Week/Month/Year/Max). Best Performing Stocks in Portfolio/ Worst performing stocks in portfolio | Infographics for real time feed for the instruments(Should be able to add upto 5 more) | Unit/Integration/regression testing;
Create a Tab for Completed Orders- Grid: Symbol/(Sell - Buy)/(Limit-Mkt)/Qty/Price/Time/Status(Open-inprogress-completed/close) | Create Grid That has columns : Description(Row: Available, Margin, Pay-in,Pay-Out, Collateral, Exposure-gauge) Value(Row: Numerical values upto two decimal points) | Holdings - Create Tabs: Current Holdings(number count), Holdings(number count); Create Radio buttons to switch between : Netwise/Daywise (Only Appears for Positions tabs for day trade executions) Create Radio buttons to switch between : MtM/PNL Basic sort by clicking on either column in grid. Create Grid That has columns : Symbol, product, Qty, Prev. Close, LTP, MTM, %Change The bottom footer shows total MTM for the day, current value of the portfolio/Total Investment.(uptown two decimal places)
Tab Trades - Grid: Symbol/(Sell - Buy)/(Limit-Mkt)/Qty/Price/Time/Status(Open-inprogress-completed/close)
Scrum:Abhinav
Pair1: Shalabh and Lu Wen
Pair2: Prithvi and Pankaj
Pair3: Manish & Hardik

## SP4
Start Date - Apr. 1 | End Date - Apr. 14
F6 - Markets | F7 - History | F8 - Fund Transfer | F9 - Alerts | F-10 Settings | Testing
Drop down to fetch by: Day's Gainers/Day's Losers/ Most Active by volume/Most Active by Value/ Volume Shockers/ Upper Circuit breakers/ Lower Circuit Breakers/ROI/52W High/ 52W Low/ Nearing 52W High/ Nearing 52W Low/ Near circuit limit - lower/Upper | Table layout of all Order Executions(by Day/Week/Month/Year) | Payment Grid for recent activities just like in a bank account for debit/credit | Marked Alerts for market instruments - create textareas like dialogue boxes and update as rss feed whenever a user defined alert is executed. | Acc Details: proof of income, SSN, Bank account details | Unit/Integration/regression testing;
The above instruments are either being traded on DJ/NQ/SP - drop down selection | Pay outs - payment debited from treading account to client account - grid containing amount(up to 2 decimal places),date,time; For day/week/month/year/max |  |  | Trade Pref: investor/day trader/option n futures
Grid with columns: (Symbol, LTP, Day's Change/% Day Change/Volume/Mkt Cap/Prev Close) | Pay-in - payment credited to trading account - grid containing amount(up to 2 decimal places),date,time; For day/week/month/year/max |  |  | Language settings to support various languages
| Charges - levid on traded instruments(default to $1 each for ease of execution) |  |  | Timezone
| Reports - from instruments for dividend payouts, voting, results etc |  |  | Password Mgmt: request to reset password/username
Theme - dark/light: font - large(16)/medium(12)/smal(9)
Scrum:Pankaj
Pair1: Manish and Lu Wen
Pair2: Hardik and Shalabh
Pair3: Abhinav & Prithvi

## SP5
Start Date - Apr. 15 | End Date - Apr. 28
F-11 Documents | F-12 Help Center | F-13 Forum | F-14 Messages | F-15 Payment Gateway | Testing
Tax Docs | Contact Us - phone number provided with hours of operations/Email/Chatbot | community chats | Client/instrument/trade/margin-call Communications | Implement Google payment Gateway | Unit/Integration/regression testing;
monthly/quaterly/yearly settlement docs | FAQ | Discord link | Div Payouts etc | Paypal
| Schedule a call - drop number, message with time of availability. |  |  | Direct Debit from Bank - with one-time or scheduled payment options
Scrum:Prithviraj
Pair1: Lu Wen and Abhinav
Pair2: Hardik and Pankaj
Pair3: Manish & Shalabh