## Sprint Planning
Project Backlog
CSE-6324 - AGILE 2022
Project Name:Trade-BnB | Web Application
Team Members: Abhinav Wadhwa, Pankaj Venkat Gope, Manish Kumar, Hardik Jain, Prithviraj Eswaramoorthy, Lu Wen, Shalabh Bajaj
Sprint | Story | No. Of Days | Status {TBC=To be Scheduled IP= In progress, or C = Complete} | Team Structure | Total Story Points=Total days of work | 50
SP1 | Login Page | 2 | Complete | Scrum:Manish | Total Sprints | 5
| Registration Page | 2 | Complete | Pair1: Prithviraj and Abhinav
| Dashboard/Landing Page | 2 | Complete | Pair2: Hardik and Pankaj | Total Sprints | Forecast-Days | Actual-Days
| Stack and Infra Planning | 1 | Complete | Pair3: Lu Wen & Shalabh | 1 | 50 | 53
| Data Island | 2 | Complete |  | 2 | 40 | 37
| Testing | 1 | Complete |  | 3 | 30 | 28
SP2 | Navigation/Roles/Routing | 3 | Complete | Scrum:Hardik | 4 | 20 | 17
| Verification/Validation | 2 | Complete | Pair1: Prithviraj and Lu Wen | 5 | 10
| Session State/cookies | 2 | Complete | Pair2: Shalabh and Pankaj
| Dashboard(Flashcards and features) | 2 | Complete | Pair3: Manish & Abhinav
| Testing | 1 | Complete
SP3 | F1 - Orders | 3 | Complete | Scrum:Abhinav
| F2 - Funds | 1 | Complete | Pair1: Shalabh and Lu Wen
| F3 - Portfolio | 2 | Complete | Pair2: Prithviraj and Pankaj
| F4 -Active Positions | 1 | Complete | Pair3: Manish & Hardik
| F5 - DJ/S&P500/Nasdaq | 2 | Complete
| Testing | 1 | Complete
SP4 | F6 - Markets | 3 | Complete | Scrum:Pankaj
| F7 - History | 2 | Complete | Pair1: Manish and Lu Wen
| F8 - Fund Transfer | 2 | Complete | Pair2: Hardik and Shalabh
| F9 - Alerts | 1 | Complete | Pair3: Abhinav & Prithvi
| F10 Settings | 1 | TBC
| Testing | 1 | Complete
SP5 | F11 Documents | 1 | TBS | Scrum:Prithviraj
| F12 Help Center | 1 | TBS | Pair1: Lu Wen and Abhinav
| F13 Forum | 3 | TBS | Pair2: Hardik and Pankaj
| F14 Messages | 1 | TBS | Pair3: Manish & Shalabh
| F15 Payment Gateway | 3 | TBS
| Testing | 1 | TBS

## SP1
Start Date - Feb. 10 | End Date - Feb. 24
US_1: Login Page | US_2: Registration Page | US_3: Dashboard/Landing Page | US_4: System design | US_5: Data Island | Testing
1. Create a login page with username and password fields. 2. User should only be able to access the application on login. 3. Authenticate the user with the registered username and password. 4. Implement the forgot password functionality. 5. Allow the user to login using gmail account.(2 way authentication - prefered) | 1. Create the registration page with fields such as name, age, email, phone number, username, password and confirm password. 2. After the user submits the registration form, an email will be sent to the registered email id. 3. User can confirm their registration by clicking on the confirmation link in the email.(In real world users are not registered until they provide a valid SSN and Bank Account number, which is sent as a seperate secure form for the user to fill after initial verification) | 1. The dashboard here refers to implementing the overall app layout:a) Create headers,b)Create footers,and c)Create Features layout. | a) Backend, b) Business logic layer, c) Gateway design, d) Frontend | 1. Create data mockup for : Frontend/Middle ware/Data dump for backend | 1. Unit/Integration/regression testing;
* Automation - if possible
Scrum:Manish
Pair1: Prithvi and Abhinav
Pair2: Hardik and Pankaj
Pair3: Lu Wen & Shalabh
Sprint Burndown Stats
Sp Start Date | 2022-02-10 | Days of sprint | Target | Actual
Sp End Date | 2022-02-24 | 0 | 320 | 320
Working Days | 10 | 1 | 288 | 296
Team Size | 7 | 2 | 256 | 256
working hours per day | 4 | 3 | 224 | 224
Total Available Hours | 280 | 4 | 192 | 192
Avg Daily Hours | 40 | 5 | 160 | 160
Avg Productivity % | 80 | 6 | 128 | 128
Productive hours | 320 | 7 | 96 | 96
Avg dDaily Productive Hours | 32 | 8 | 64 | 64
|  | 9 | 32 | 32
|  | 10 | 0 | 0

## SP2
Start Date - Feb. 25 | End Date - Mar. 10
US_6: Navigation/Roles/Routing | US_7: Validation | US_8: Session State/cookies | US_9: Dashboard(Flashcards and features) | Testing
Create Navigation, Provide access based on roles/priviliges; setup routing schema between pages pased on priviliges | Validate a user: name - should only contain upper and lower case letters. Two separate fields for given name and Surname age - should only contain numeric values email - must be a valid email (eg. user@domain.com) phone number - should only contain numeric values (length 10 characters) username - must be unique, should only contain alphabets or numbers password - min 8 chars, must be a combination of alphabets, numeric and special characters(passwords are masked at all times) confirm password - this value must match with the password field | Maintain session state using jpt-tokens. Validity till infinity(feature with auto renewal) | Watchlist - available at all times towards the right.(Page layout 70:30) - can have upto 10 using add button and a name for each watch list. Within each watch list can add upto 20 elements. Dedicated shortcuts/Overview to Account Summary, Orders, Current positions, Infographics for - DJ,S&P,NQ/ Breaking news impacting stocks in action(active by volume/value) It should be customizable to Add/Del other elements | Unit/Integration/regression testing;
Scrum:Hardik
Pair1: Shalabh and Pankaj
Pair2: Prithvi and Lu Wen
Pair3: Manish & Abhinav

## SP3
Start Date - March 28 | End Date - April 07
US_10: Orders | US_11: Funds | US_12: Portfolio | US_13: Active Positions | US_14: DJ/S&P500/Nasdaq | Testing
Create a Tab for Pending Orders - Grid: Symbol/(Sell - Buy)/(Limit-Mkt)/Qty/Price/Time/Status(Open-inprogress-completed/close) | Create Pay-In/Pay-Out Controls which redirect to third party payment gateway links | Create Tabs: Current Holdings(number count), Holdings(number count); Create Radio buttons to switch between : Netwise/Daywise (Only Appears for Positions tabs for day trade executions) Create Radio buttons to switch between : MtM/PNL Basic sort by clicking on either column in grid. Create Grid That has columns : Symbol, product, Qty, Prev. Close, LTP, MTM, Buy Avg., Sell Avg The bottom footer shows total MTM for the day | Dashboard shortcut for active positions, Total Investment vs Total PNL, Infographics for performance of portfolio over (Day/Week/Month/Year/Max). Best Performing Stocks in Portfolio/ Worst performing stocks in portfolio | Infographics for real time feed for the instruments(Should be able to add upto 5 more) | Unit/Integration/regression testing;
Create a Tab for Completed Orders- Grid: Symbol/(Sell - Buy)/(Limit-Mkt)/Qty/Price/Time/Status(Open-inprogress-completed/close) | Create Grid That has columns : Description(Row: Available, Margin, Pay-in,Pay-Out, Collateral, Exposure-gauge) Value(Row: Numerical values upto two decimal points) | Holdings - Create Tabs: Current Holdings(number count), Holdings(number count); Create Radio buttons to switch between : Netwise/Daywise (Only Appears for Positions tabs for day trade executions) Create Radio buttons to switch between : MtM/PNL Basic sort by clicking on either column in grid. Create Grid That has columns : Symbol, product, Qty, Prev. Close, LTP, MTM, %Change The bottom footer shows total MTM for the day, current value of the portfolio/Total Investment.(uptown two decimal places)
Tab Trades - Grid: Symbol/(Sell - Buy)/(Limit-Mkt)/Qty/Price/Time/Status(Open-inprogress-completed/close)
Scrum:Abhinav
Pair1: Shalabh and Lu Wen
Pair2: Prithvi and Pankaj
Pair3: Manish & Hardik

## SP4
Start Date - Apr. 8 | End Date - Apr. 21
F6 - Markets | F7 - History | F8 - Fund Transfer | F9 - Alerts | F-10 Settings | Testing
Drop down to fetch by: Day's Gainers/Day's Losers/ Most Active by volume/Most Active by Value/ Volume Shockers/ Upper Circuit breakers/ Lower Circuit Breakers/ROI/52W High/ 52W Low/ Nearing 52W High/ Nearing 52W Low/ Near circuit limit - lower/Upper | Table layout of all Order Executions(by Day/Week/Month/Year) | Payment Grid for recent activities just like in a bank account for debit/credit | Marked Alerts for market instruments - create textareas like dialogue boxes and update as rss feed whenever a user defined alert is executed. | Acc Details: proof of income, SSN, Bank account details | Unit/Integration/regression testing;
The above instruments are either being traded on DJ/NQ/SP - drop down selection | Pay outs - payment debited from treading account to client account - grid containing amount(up to 2 decimal places),date,time; For day/week/month/year/max |  |  | Trade Pref: investor/day trader/option n futures
Grid with columns: (Symbol, LTP, Day's Change/% Day Change/Volume/Mkt Cap/Prev Close) | Pay-in - payment credited to trading account - grid containing amount(up to 2 decimal places),date,time; For day/week/month/year/max |  |  | Language settings to support various languages
| Charges - levid on traded instruments(default to $1 each for ease of execution) |  |  | Timezone
| Reports - from instruments for dividend payouts, voting, results etc |  |  | Password Mgmt: request to reset password/username
Theme - dark/light: font - large(16)/medium(12)/smal(9)
Scrum:Pankaj
Pair1: Manish and Lu Wen
Pair2: Hardik and Shalabh
Pair3: Abhinav & Prithvi

## SP5
Start Date - Apr. 15 | End Date - Apr. 28
F-11 Documents | F-12 Help Center | F-13 Forum | F-14 Messages | F-15 Payment Gateway | Testing
Tax Docs | Contact Us - phone number provided with hours of operations/Email/Chatbot | community chats | Client/instrument/trade/margin-call Communications | Implement Google payment Gateway | Unit/Integration/regression testing;
monthly/quaterly/yearly settlement docs | FAQ | Discord link | Div Payouts etc | Paypal
| Schedule a call - drop number, message with time of availability. |  |  | Direct Debit from Bank - with one-time or scheduled payment options
Scrum:Prithviraj
Pair1: Lu Wen and Abhinav
Pair2: Hardik and Pankaj
Pair3: Manish & Shalabh